## Invoicing
| Scheduled for Build | 474008.8
| Needs to be Invoiced | 39552.89
| Money Invoiced /Owed | 341545.425
| Total | 855107.115
Scheduled for Build |  |  | 474008.8 |  | NEEDS TO BE INVOICED |  |  |  |  | 39552.89 | INVOICED |  |  |  |  | Balance Due | 341545.425
Scheduled Build Date | Homeowner | PM | Insurance / Retail | Before Build Total | Scheduled Build Date | Homeowner | PM | Insurance / Retail | Before Build Total | Notes | Scheduled Build Date | Homeowner | PM | Insurance / Retail | Before Build Total | After Build Total | Payments Received | Balance Due | Notes
2026-05-28 | Rich Cosgrove | Will | R | 60608.31 | 2026-07-23 | Don Byrnes Roof | John | I | 19311.94 | 8/21 he died :( waiting till skylight is done | 2026-08-10 | Ken Gilchrist | John | I | 55139.74 | 56774.56 |  | 56774.56 | 9/4 note to john
2026-08-14 | Chelsea Fingerhut | Megan | R | 24499.8 | 2026-08-12 | Joe Schutt Siding | John | I | 20240.95 | 8/21 needs more work done :( | 2026-07-11 | Denise Kaluba | Jamie | I | 30311.46 | 34863.44 |  | 34863.44 | 8/31 should be getting paid this week
2026-08-21 | Heather Cook | John | R | 2047.86 | [6 empty] | 2026-08-07 | Eric Wagner Siding | John | I | 32506.83 | 34331.22 |  | 34331.22 | 9/3 Left a voicemail
2026-08-22 | Coury Richards Roof | John | I | 16872.56 | [6 empty] | 2026-08-03 | Dan Gutwein | Megan | R | 19597.42 | 28558.43 |  | 28558.43 | 9/4 resent invoice
2026-08-25 | Rachel Byrnes Siding | John | I | 21617.88 | [6 empty] | 2026-09-01 | Mirko Paulic | Jamie | I | 23082.08 | 27927.08 |  | 27927.08 | 9/9 Funds should be released in a few days
2026-08-31 | Coury Richards Siding | John | I | 9322.6 | [6 empty] | 2026-08-21 | Diana Gruber 2756 | Mike | R | 27692.31 | 27692.31 |  | 27692.31 | 9/2 she will mail a check in
2026-09-02 | Mitchell Ayers | John | R | 14359.53 | [6 empty] | 2026-06-09 | John Stavros | Will | R | 17911.09 | 18336.09 |  | 18336.09 | 8/31 Waiting for check to get signed then bringin $$ in
2026-09-01 | Shree Kurup | Megan | R | 42937.21 | [6 empty] | 2026-08-31 | Ed Grabowski Roof | Jamie | I | 17908.98 | 18158.09 |  | 18158.09 | 9/8 invoice sent
2026-09-03 | John Kish Siding | Jamie | I | 60305.99 | [6 empty] | 2026-08-29 | Jessica Jacob | Dani | I | 17152.79 | 23137.77 | 8576.39 | 14561.38 | 9/8 First payment should be paid by Friday 9/11
2026-09-03 | Kathy Scheiring | George | R | 7043.7 | [6 empty] | 2026-06-16 | Linda McNellis-Caldwell | John | R | 12706.1 | 12706.1 |  | 12706.1 | 9/8 She is going to call the Trust people for an update
2026-09-03 | Alison Dusz | John | R | 3936.4 | [6 empty] | 2026-08-29 | Shannon Story | Dani | I | 11253.37 | 11295.55 |  | 11295.55 | 9/2 Sent initial invoice text
2026-09-04 | Stuart Leemaster | Jamie | I | 23547.15 | [6 empty] | 2026-08-24 | Brandon Bail Roof | Andrew | I | 10951.19 | 10951.19 |  | 10951.19 | 9/3 Left a voicemail
2026-09-04 | Karla Mahoney Siding | John | I | 28307.55 | [6 empty] | 2026-05-14 | Darrell Chambers | George | I | 12974.62 | 13192.37 | 2499 | 10693.37 | 9/2 Left a voicemail and sent a text
2026-09-08 | Becky Zickefoose | Jamie | R | 3717.88 | [6 empty] | 2026-07-30 | Trena Wright | Dani | R | 10483.41 | 9755.41 |  | 9755.41 | 9/1 Richard said it will be paid by the 15th
2026-09-08 | Sonny Lenaers Roof | George | I | 37462.64 | [6 empty] | 2026-08-26 | Madison Williams | George | I | 25334.45 | 27057.37 | 21545.4 | 5511.97 | 9/1 1st payment received
2026-09-11 | Gloria Morgan Roof | Megan | I | 11772.58 | [6 empty] | 2026-08-15 | Matthew Cox Siding | John | R | 14743.42 | 14743.42 | 9400.12 | 5343.3 | 8/27 turns out this is insurance. eye roll.
2026-09-09 | Dartisha Thompson Roof | George | I | 9243.9 | [6 empty] | 2026-05-27 | Allison Lenner Roof | John | I | 10858.28 | 12116.7 | 8382.76 | 3733.94 | 8/27 message to Kenny to see if siding can be done soon
2026-09-10 | Darryl Wagner | Andrew | R | 15984.87 | [6 empty] | 2026-08-21 | Jenna Shaw | Andrew | R | 2955.14 | 2955.14 |  | 2955.14 | 9/9 Left her a voicemail. Tagged Mike and Andrew
2026-09-10 | Teresa Albainy | Megan | R | 20188.12 | [6 empty] | 2026-06-05 | Meghan Lewis | Dani | I | 25049.47 | 25049.47 | 22549.47 | 2500 | 9/2 Account got hacked. Gets paid on the 11th
2026-09-11 | George Kiarie Roof | Andrew | I | 8231.1 | [6 empty] | 2026-08-31 | Emily Washington | Dani | R | 6493.58 | 6643.58 | 5000 | 1643.58 | 9/2 1st payment received
2026-09-12 | Andy Kramer | John | R | 8834.79 | [6 empty] | 2026-08-24 | Joe Heinen | George | R | 1334.86 | 1334.86 |  | 1334.86 | 9/2 emailed him the invoice again
2026-09-14 | Gina Grinnell | Dani | I | 18622.28 | [6 empty] | 2026-08-18 | Hannah Tabory | John | I | 4528.32 | 5008.77 | 3708.48 | 1300.29 | 9/8 Hannah should receive check by Friday 9/11
2026-09-14 | Alan Figiel Roof | Andrew | I | [7 empty] | 2026-04-08 | Michael Litten | Dani | I | 8450.45 | 9124.61 | 8506.485 | 618.125 | 9/4 Sent a text
2026-09-15 | Chris Simmons | Dani | I | 12549.06 | [6 empty] | 2026-08-03 | Shawn Simon | Andrew | R | 67930.76 | 67930.76 | 67930.76 | 0
2026-09-19 | James Tarnay | Andrew | R | 11995.04 | [6 empty] | 2026-09-02 | Eric Hansen | John | R | 5455.74 | 5455.74 | 5455.74 | 0
[11 empty] | 2026-08-24 | Ann Work | George | R | 5104.29 | 5236.52 | 5236.52 | 0
[11 empty] | 2026-08-12 | James Desmarteau | Jamie | R | 12896.11 | 13148.11 | 13148.11 | 0
[11 empty] | 2026-08-31 | Larry Sluder | Jamie | R | 7997.51 | 7997.51 | 7997.51 | 0 | 9/2 closes out next week
[11 empty] | 2026-08-13 | Michael Burgess | John | R | 9940.75 | 11740.75 | 11740.75 | 0 | 9/2 work is being finished on 9/9
[11 empty] | 2026-08-31 | Michael Polarinakis | Mike | R | 18207.22 | 18207.22 | 18207.22 | 0 | 9/2 closes out next week
[11 empty] | 2026-09-03 | Elizabeth Vensade | Megan | R | 15441.7 | 15441.7 | 15441.7 | 0 | 9/9 Paid in full

## Sheet2
pg 11 | 23968.18 | pg 12 | 6196.22 | pg 13 | 142.52 |  | acv | dep | rcv
deductible | 4090 |  |  |  |  | 23-30 | -780.24 | -300.81 | -1081.05
acv | 16186.02 | acv | 5373.93 | acv | 121.72 | 33 | -44.52 | -23.12 | -67.64
depreciation | 3692.16 | depreciation | 804.78 | depreciation | 20.8 | 50-51 | -121.72 | -20.8 | -142.52
|  | non recov dep | 17.51 |  |  | 52 | -53.78 | -17.51 | -71.29
[6 empty] | 53 | -156.55 | 0 | -156.55
[7 empty] | -1156.81 | -362.24 | -1519.05
-17.51