## Invoicing
| Scheduled for Build | 488694.26
| Needs to be Invoiced | 194999.35
| Money Invoiced /Owed | 251643.585
| Total | 935337.195
Scheduled for Build |  |  | 488694.26 |  | NEEDS TO BE INVOICED |  |  |  |  | 194999.35 | INVOICED |  |  |  |  | Balance Due | 251643.585
Scheduled Build Date | Homeowner | PM | Insurance / Retail | Before Build Total | Scheduled Build Date | Homeowner | PM | Insurance / Retail | Before Build Total | Notes | Scheduled Build Date | Homeowner | PM | Insurance / Retail | Before Build Total | After Build Total | Payments Received | Balance Due | Notes
2026-05-28 | Rich Cosgrove | Will | R | 60608.31 | 2026-07-23 | Don Byrnes Roof | John | I | 19311.94 | 8/21 he died :( waiting till skylight is done | 2026-06-09 | Anavelez Rodriguez Roof | George | I | 19052.93 | 19567.54 | 19567.54 | 0 | closing out with the siding
2026-07-23 | Paul Dechellis | John | R | 3620.45 | 2026-08-13 | Michael Burgess | John | R | 9940.75 | 8/20 note to john | 2026-07-31 | Chad Schleh | Andrew | R | 7322.98 | 7322.98 | 7322.98 | 0 | 8/18 seth will call abc to sort it out so we can close
2026-08-03 | Shawn Simon | Andrew | R | 67930.76 | 2026-08-12 | Joe Schutt Siding | John | I | 20240.95 | 8/21 needs more work done :( | 2026-08-05 | Nathan Molitor | Megan | I | 19734.11 | 19904.11 | 19904.11 | 0
2026-08-14 | Chelsea Fingerhut | Megan | R | 24499.8 | 2026-08-17 | Cynthia Moffit Roof | John | I | 33302.96 | 8/20 note to john | 2026-08-05 | Bobby VerBrugge | John | R | 13740.45 | 14165.45 | 14165.45 | 0
2026-08-20 | JoAnn Abbadini Siding | John | I | 20226.38 | 2026-08-01 | Brent Peters | Megan | R | 15692.34 | 8/21 gutters get done today | 2026-08-17 | Kim Potts | Andrew | R | 2163.74 | 2163.74 | 2163.74 | 0
2026-08-21 | Jim Conner | Mike | R | 50480.77 | 2026-08-17 | Mark Fleming | Dani | R | 38024.73 | 8/21 note to dani and mike | 2026-08-19 | Pinaki Chaudhuri | Jamie | R | 3470.81 | 3470.81 | 3470.81 | 0
2026-08-21 | Jenna Shaw | Andrew | R | 2955.14 | 2026-08-10 | Ken Gilchrist | John | I | 55139.74 | 8/21 should be getting today | 2026-08-19 | Jen Gomez | Andrew | R | 3333.76 | 3333.76 | 3333.76 | 0
2026-08-21 | Elva McKee | George | R | 2335.95 | 2026-08-19 | Robyn Sims | Megan | R | 3345.94 | 8/21 folder to meg | 2026-08-18 | Navaro Nation Roof | George | I | 9702.98 | 9702.98 | 9702.98 | 0
2026-08-21 | Heather Cook | John | R | 2047.86 | [6 empty] | 2026-04-08 | Michael Litten | Dani | I | 8450.45 | 9124.61 | 8506.485 | 618.125 | 8/10 sent Mike a text, asking if mortgage company got the check
2026-08-22 | Donna Fern | Jamie | Retail | 9939.82 | [6 empty] | 2026-07-09 | April Deditch | Dani | R | 14867.85 | 15848.27 | 14863 | 985.27 | 8/17 Waiting on final check to come in
2026-08-22 | Coury Richards Roof | John | I | 16872.56 | [6 empty] | 2026-08-13 | Emma Hutchinson | Megan | R | 3099.76 | 3099.76 | 1800 | 1299.76 | 8/21 note to megan. this got screwed up.
2026-08-24 | Mitchell Ayers | John | R | 18059.08 | [6 empty] | 2026-08-18 | Hannah Tabory | John | I | 4528.32 | 5008.77 | 3708.48 | 1300.29 | 8/20 1st payment rececived
2026-08-24 | Brandon Bail Roof | Andrew | I | 10951.19 | [6 empty] | 2026-08-11 | Diana Gruber | Mike | R | 1525.66 | 1525.66 |  | 1525.66 | 8/12 invoice sent
2026-08-24 | Becky Zickefoose | Jamie | R | 3717.88 | [6 empty] | 2026-06-05 | Meghan Lewis | Dani | I | 25049.47 | 25049.47 | 22549.47 | 2500 | 8/19 Check dropped off. Coming again next week
2026-08-24 | Ann Work | George | R | 5104.29 | [6 empty] | 2026-05-27 | Allison Lenner Roof | John | I | 10858.28 | 12116.7 | 8382.76 | 3733.94 | 8/6 will pay in full when the siding is complete
2026-08-24 | Paul Dechellis | John | R | 3620.45 | [6 empty] | 2026-08-08 | James Golden | Megan | I | 8878.35 | 8878.35 | 4710 | 4168.35 | 8/12 1st payment received
2026-08-24 | Matthew Fieldman | George | R | 1666.14 | [6 empty] | 2026-08-18 | Cynthia Schutt Malhina | Andrew | R | 5047.48 | 5217.48 |  | 5217.48 | 8/21 invoice sent
2026-08-25 | Rachel Byrnes Siding | John | I | 21617.88 | [6 empty] | 2026-08-15 | Matthew Cox Siding | John | R | 5343.3 | 5343.3 |  | 5343.3 | 8/21 invoice sent
2026-08-26 | Madison Williams | George | I | 25334.45 | [6 empty] | 2026-08-18 | Jenny Goodman | John | R | 5829.61 | 5829.61 |  | 5829.61 | 8/18 invoice sent
2026-08-27 | Jessica Jacob | Dani | I | 17152.79 | [6 empty] | 2026-07-30 | Tyrell Weinmann | Jamie | R | 15390.83 | 16052.65 | 10000 | 6052.65 | 8/21 sent updated invoice
2026-08-28 | Shannon Story | Dani | I | 11253.37 | [6 empty] | 2026-08-19 | Joshua Foss Roof | George | I | 7685.58 | 8557.23 |  | 8557.23 | 8/21 invoice sent
2026-09-01 | Shree Kurup | Megan | R | 42937.21 | [6 empty] | 2026-07-23 | Kyle Breiding | Andrew | I | 17335.28 | 20702.72 | 11692.43 | 9010.29 | 8/18 ins needs to release the funds
2026-09-02 | Eric Hansen | John | R | 5455.74 | [6 empty] | 2026-07-20 | Ryan Chaw | George | R | 9028.32 | 9032.96 |  | 9032.96 | 8/18 asking George to call
2026-09-07 | John Kish Siding | Jamie | I | 60305.99 | [6 empty] | 2026-07-30 | Trena Wright | Dani | R | 10483.41 | 9755.41 |  | 9755.41 | 8/17 Have not received check from insurance
| Emily Washington | Dani | R | [7 empty] | 2026-05-14 | Darrell Chambers | George | I | 12974.62 | 13192.37 | 2499 | 10693.37 | 8/19 Tried calling but mailbox is full
[11 empty] | 2026-08-08 | Beverly Rambert Roof | Jamie | I | 10999.53 | 10999.53 |  | 10999.53 | 8/17 Paying by Thursday
[11 empty] | 2026-06-16 | Linda McNellis-Caldwell | John | R | 12706.1 | 12706.1 |  | 12706.1 | 8/20 emailed invoice
[11 empty] | 2026-06-29 | Irving Rodriguez Siding | George | I | 25538.43 | 29721.78 | 16644.81 | 13076.97 | 8/18 George needs to call the insurance company
[11 empty] | 2026-08-12 | James Desmarteau | Jamie | R | 12896.11 | 13148.11 |  | 13148.11 | 8/21 he will mail in a partial payment
[11 empty] | 2026-06-09 | John Stavros | Will | R | 17911.09 | 18336.09 |  | 18336.09 | 8/19 Left him a voicemail
[11 empty] | 2026-08-03 | Dan Gutwein | Megan | R | 19597.42 | 28558.43 |  | 28558.43 | 8/17 invoice sent
[11 empty] | 2026-08-07 | Eric Wagner Siding | John | I | 32506.83 | 34331.22 |  | 34331.22 | 8/18 Follow up 8/21 if no payment is made
[11 empty] | 2026-07-11 | Denise Kaluba | Jamie | I | 30311.46 | 34863.44 |  | 34863.44 | 8/20 invoice sent

## Sheet2
pg 11 | 23968.18 | pg 12 | 6196.22 | pg 13 | 142.52 |  | acv | dep | rcv
deductible | 4090 |  |  |  |  | 23-30 | -780.24 | -300.81 | -1081.05
acv | 16186.02 | acv | 5373.93 | acv | 121.72 | 33 | -44.52 | -23.12 | -67.64
depreciation | 3692.16 | depreciation | 804.78 | depreciation | 20.8 | 50-51 | -121.72 | -20.8 | -142.52
|  | non recov dep | 17.51 |  |  | 52 | -53.78 | -17.51 | -71.29
[6 empty] | 53 | -156.55 | 0 | -156.55
[7 empty] | -1156.81 | -362.24 | -1519.05
-17.51